## Sheet1
NAPTF Construction Cycle Data Collection - CC9 Rut Depth Measurement
Site: | CC9 | Test: | Weekly Trafficking |  | Task Order: | 003, 005
Date: | 2021-07-14 | Time: | 9:15 |  | Deliverable: | 5.1.63 (003)
Operators: | J Landy Jr / H Fermin
Standard: | ASTM E1703 Standard Test Method for Measuring Rut Depth of Pavement Surfaces
Equipment: | 16 ft. straightedge, rut depth measurement gauge
Instructions: | Make sure straigthedge is marked at centerline and at 1 ft. increments.
Record the fully extended gauge length.
Place the straightedge on the pavement perpendicular to traffic direction.
Align the center of the straightedge with the center line of the wander path along the station line at the desired testing location.
Locate the point of maximum rut depth. Record the rut depth measurement and offset location.
Units and Formats: | Station | Offset |  | Rut Depth
| Feet | Feet and Inches |  | Inches
| 0+15 | +15.00' |  | 0.100"
Notes: | Wander 2 of 8
Fully Extended Gauge Length: |  |  | 0.989
Station | Side of Test Section | Centerline of Test Location |  | Maximum Rut Depth |  | Offset Location of Max Rut Depth
Station 0+15 | South | +15'-0"
Station 0+30 | South | +15'-0"
Station 0+75 | South | +15'-0"
Station 0+90 | South | +15'-0"
Station 1+35 | South | +15'-0"
Station 1+50 | South | +15'-0"
Station 1+95 | South | +15'-0"
Station 2+10 | South | +15'-0"
Station 2+55 | South | +15'-0" |  | 0.632 |  | 12.5
Station 2+70 | South | +15'-0" |  | 0.805 |  | 13.7
Station | Side of Test Section | Centerline of Test Location |  | Maximum Rut Depth |  | Offset Location of Max Rut Depth
Station 0+15 | North | -15'-0" |  |  |  | -
Station 0+30 | North | -15'-0" |  |  |  | -
Station 0+75 | North | -15'-0" |  |  |  | -
Station 0+90 | North | -15'-0" |  |  |  | -
Station 1+35 | North | -15'-0" |  |  |  | -
Station 1+50 | North | -15'-0" |  |  |  | -
Station 1+95 | North | -15'-0" |  |  |  | -
Station 2+10 | North | -15'-0" |  |  |  | -
Station 2+55 | North | -15'-0" |  | 0.843 |  | -17.60
Station 2+70 | North | -15'-0" |  | 0.793 |  | -17.70